## Slide 1
ConnectEd: Transforming Bridgewood Academy into a Digital Learning Pioneer
A business case for transitioning to a fully digital learning model that will modernise our institution, expand our reach, and secure our future in the evolving educational landscape.

## Slide 2
Project Overview: The Digital Transformation Journey
Bridgewood Academy stands at a critical juncture. Our objective is to transition from a traditional campus-based model to a fully digital adult education experience that meets the demands of today's learners.
This transformation aligns with our institutional vision to become a leader in accessible, flexible education while addressing the financial challenges facing the traditional education sector.
Modernise Learning Delivery
Implement cutting-edge digital teaching methods and platforms that reflect contemporary learning preferences.
Expand Geographic Access
Remove location barriers to education, enabling nationwide and potentially global student recruitment.
Reduce Operational Costs
Eliminate expensive physical infrastructure while optimising resource allocation.
Improve Learner Satisfaction
Provide flexible, accessible education that adapts to adult learners' busy schedules and diverse needs.

## Slide 3
Business Options Analysis
Do Nothing
Advantages: No immediate disruption to operations or staff
Disadvantages: Continued decline in enrolment, unsustainable operational costs, gradual loss of market relevance, and falling behind competitors
Do Minimum
Advantages: Gradual transition with lower implementation risk, partial cost savings
Disadvantages: Complex hybrid operations, limited financial savings, extended transition period, and potential confusion for learners
Do Something (Recommended)
Advantages: Complete transition to cost-effective and scalable digital model, strategic positioning, maximum savings
Disadvantages: Higher initial investment, significant organisational change, temporary disruption

## Slide 4
Benefits & Dis-benefits Analysis
Benefits
£300K
Annual Savings
Reduction in facility and operational costs
£90K
Revenue Growth
Increased tuition from expanded reach
30%
Enrolment Increase
Projected growth in student numbers
25%
Satisfaction Rise
Anticipated improvement in learner experience
Dis-benefits
Staff Impact
Campus support staff redundancies requiring careful management and potential retraining opportunities
Digital Adaptation
Adjustment period for both staff and students to master new digital learning environment
In-Person Interaction
Loss of traditional face-to-face learning environment and social community aspects

## Slide 5
Key Risks & Mitigation Strategies
Risk
Likelihood
Impact
Mitigation Strategy
Staff resistance to digital transition
High
High
Comprehensive change management programme, retraining opportunities, early involvement in planning
Technical platform issues
Medium
High
Rigorous vendor vetting, phased rollout, robust testing, and fallback options
Negative public relations
Medium
Medium
Transparent communication strategy, focus on improved accessibility and quality
Low digital platform uptake
Medium
High
Dedicated learner onboarding support, intuitive design, early adopter incentives
Our risk assessment identifies staff resistance and potential technical issues as our highest priority concerns, with comprehensive mitigation strategies in place for all identified risks.

## Slide 6
Implementation Costs & Timeline
Cost Breakdown
Category
Amount (£)
Development & Technology
59,200
Training & Setup
30,000
Lecturer Wages (Y1)
120,000
Contingency
25,000
Total Cost: £234,200
12-Week Implementation Timeline
1
Weeks 1-2: Planning
Finalise requirements, select vendors, secure approvals
2
Weeks 3-5: Development
Platform configuration, content migration, testing
3
Weeks 6-7: Staff Transition
Training programmes, new role assignments
4
Weeks 8-9: Closure & Setup
Campus transition, final platform preparations
5
Week 10: Go Live
Platform launch, initial student onboarding
6
Weeks 11-12: Evaluation
Performance assessment, adjustments, reporting

## Slide 7
Investment Appraisal: The Financial Case
Key Financial Metrics
First-Year ROI: 66.5% (Outstanding return on investment within 12 months)
Years to Payback: 0.6 years (Investment recovered in just over 7 months)
Annual Benefit: £390K (Combined revenue increase and cost savings)
Non-Financial Benefits
Enhanced institutional reputation as an educational innovator
Strategic flexibility to respond to changing educational landscape
Improved learner satisfaction through accessibility and convenience
Reduced environmental impact through decreased physical operations
Data-driven insights to continuously improve educational offerings

## Slide 8
Deliverables & Governance: Ensuring Success
Major Deliverables
Integrated Digital PlatformComprehensive learning management system with seamless user experience
Modular & Mobile-Ready CoursesRedesigned curriculum optimised for digital delivery across all devices
Virtual Classroom & AnalyticsInteractive learning environments with robust performance tracking
Cybersecurity FrameworkComprehensive data protection and privacy compliance measures
Governance Structure
Business Case Owner: Director of Transformation
Project Board: Executive Leadership, Learner Services Director, Head of IT
Critical Review Points:
Week 2: Planning phase sign-off and resource allocation
Week 9: Go-live readiness assessment and final approval
Week 12: Post-implementation review and benefits realisation
Regular weekly progress reporting to ensure timely identification and resolution of any issues.